## Prabha
CHATBOT-RECAST.AI
S.no | Name | Date | Time | Project Task | Status
1 | Prabha | 12.12.2017 |  | Absent | incomplete
2 | Prabha | 13.12.2017 | 8.30 to 4.30 | created a demo bot using recast.ai learned | completed
|  |  |  | basics from recast.ai documentation entities,intents,use | completed
|  |  |  | the console. | completed
3 | Prabha | 14.12.2017 | 8.30 to 4.30 | watched videos to build a conversation tried to build a simple conversation | completed
4 | Prabha | 15.12.2017 | 8.30 to 4.45 | demo on build conversation and learned deeply about trigger and conditions | completed
5 | Prabha | 18.12.2017 | 8.30 to 4.15 | runtime API,send a message,SDks | completed
6 | Prabha | 19.12.2017 | 8.30 to 4.30 | recast.ai tutorials -documentation for creating a bot,build and connect | completed
7 | Prabha | 20.12.2017 | 8.30 to 4.30 | learned about build tab and worked on trigger,requirement,actions | completed
8 | Prabha | 21.12.2017 | 8.30 to 4.30 | created a demo bot ,learned to give notions and developed a coversation | completed
9 | prabha | 22.12.2017 | 8.30 to 4.00 | created conversational flow for demo bot | completed
10 | Prabha | 26.12.2017 | 8.30 to 4.15 | created a medicine bot demo with a conversational flow | completed
11 | Prabha | 27.12.2017 | 8.30 to 4.30 | added some enhancement to medicine bot ,created a conversation | completed
12 | Prabha | 28.12.2017 | 8.30 to 4.30 | introduction to API,documentation-responses,authentication,searched videos for API | completed
13 | Prabha | 29.12.2017 |  | Absent | incomplete
14 | Prabha | 02.01.2018 | 8.30 to 4.45 | project structural flow,process flow,api documentation | completed
15 | Prabha | 03.01.2018 | 8.30 to 4.45 | php queries,attend chatbot class,json | completed
16 | Prabha | 04.01.2018 | 8.40 to 4.45 | searched videos for API connection,json | completed
17 | Prabha | 05.01.2018 | 8.40 to 1.00 | preparing process flow | completed
18 | Prabha | 08.01.2018 | 8.30 to 3.45 | connecting bot,JSON with PHP | completed
19 | Prabha | 09.01.2018 | 8.30 to 3.30 | enhancement in flow ,learning php queries | completed
20 | Prabha | 10.01.2018 |  | Absent | incomplete
21 | Prabha | 11.01.2018 | 8.30 to 4.00 | bot builder API,bot connector-conversational states | completed